## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Doe | Completed
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | Jane Smith | In Progress
Design Phase | 2024-03-16 | 2024-03-25 | 10 | Mike Johnson | Not Started
Development Phase | 2024-03-26 | 2024-04-15 | 20 | Sarah Lee | Not Started
Testing & Quality Assurance | 2024-04-16 | 2024-04-30 | 15 | David Brown | Not Started
Deployment & Launch | 2024-05-01 | 2024-05-03 | 3 | Lisa White | Not Started