## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Priority
Project Kickoff Meeting | Alice Johnson | 2024-03-01 | 2024-03-01 | 1 | Completed | High
Market Research & Analysis | Bob Smith | 2024-03-02 | 2024-03-15 | 14 | In Progress | High
Product Design Finalization | Carol Lee | 2024-03-16 | 2024-03-31 | 16 | Planned | Medium
Development Sprint 1 | David Kim | 2024-04-01 | 2024-04-15 | 15 | Not Started | High
User Testing & Feedback Loop | Eva Martinez | 2024-04-16 | 2024-05-05 | 21 | Planned | Medium
Final Review & Deployment | Frank White | 2024-05-06 | 2024-05-10 | 5 | Not Started | High