## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed | 100
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analysts | In Progress | 60
Design Phase | 2024-03-16 | 2024-04-10 | 35 | UI/UX Team | Not Started | 0
Development Phase | 2024-04-11 | 2024-06-30 | 81 | Development Team | Not Started | 0
Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 | QA Team | Not Started | 0
Deployment & Go-Live | 2024-08-01 | 2024-08-15 | 15 | Operations Team | Not Started | 0
Post-Implementation Review | 2024-08-16 | 2024-08-20 | 5 | Project Manager | Not Started | 0