## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Notes
Project Initiation | John Doe | 2024-03-01 | 2024-03-05 | 5 | In Progress | - | Define project scope, objectives, and stakeholders.
Requirements Gathering | Jane Smith | 2024-03-06 | 2024-03-15 | 10 | Not Started | Project Initiation | Interview key users and collect functional requirements.
Design Phase | Mike Johnson | 2024-03-16 | 2024-03-31 | 16 | Planned | Requirements Gathering | Create wireframes and UI mockups.
Development | Team A | 2024-04-01 | 2024-05-15 | 65 | Not Started | Design Phase | Build core features and integrate modules.
Testing & Quality Assurance | Lisa Chen | 2024-05-16 | 2024-05-31 | 16 | Planned | Development | Conduct unit, integration, and user acceptance tests.
Deployment | Admin Team | 2024-06-01 | 2024-06-03 | 3 | Not Started | Testing & QA | Launch the solution to production environment.
Post-Deployment Review | Project Manager | 2024-06-04 | 2024-06-05 | 2 | Not Started | Deployment | Evaluate performance, gather feedback, and document lessons learned.