## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed | None
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analyst | In Progress | Kickoff Meeting
Design Phase | 2024-03-16 | 2024-04-10 | 35 | UI/UX Designer | Not Started | Requirements Gathering
Development Phase | 2024-04-11 | 2024-06-30 | 81 | Development Team | Not Started | Design Phase
Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 | QA Engineer | Not Started | Development Phase
Deployment & Go-Live | 2024-08-01 | 2024-08-05 | 5 | IT Operations | Not Started | Testing & QA
Post-Deployment Review | 2024-08-06 | 2024-08-06 | 1 | Project Manager | Not Started | Deployment & Go-Live