## Worksheet
Project Management - Schedule Planner (Tracking View)
Task ID | Task Name | Start Date | End Date | Status | Progress % | Responsible Person | Dependencies
T001 | Project Initiation Phase | 2024-01-15 | 2024-01-30 | Completed | 100% | Jane Smith
T002 | Requirements Gathering | 2024-02-01 | 2024-02-15 | In Progress | 65% | John Doe | T001
T003 | Design Phase | 2024-02-16 | 2024-03-15 | Not Started | 0% | Lisa Chen | T002
T004 | Development Phase | 2024-03-16 | 2024-05-31 | Not Started | 0% | Marcus Taylor | T003
T005 | Testing & Quality Assurance | 2024-06-01 | 2024-07-15 | Not Started | 0% | Sophie Kim | T004
T006 | Deployment & Handover | 2024-07-16 | 2024-08-31 | Not Started | 0% | Alex Rivera | T005