## Worksheet
Task ID | Task Name | Owner | Priority | Due Date | Status | Progress (%) | Dependencies | Estimated Hours | Actual Hours
PM-001 | Project Kickoff Meeting | Jane Smith | High | 2023-10-05 | Completed | 100% | -- | 4 | 4
PM-002 | Requirements Gathering | John Doe | High | 2023-10-15 | In Progress | 75% | PM-001, PM-003 | 20 | 12
PM-003 | Design Phase Initiation | Lisa Chen | Middle | 2023-11-01 | Not Started | 0% | PM-002 | 35 | 0
PM-004 | Development Sprint 1 | Mike Brown | High | 2023-11-15 | Planned | 0% | PM-003, PM-005 | 45 | 0