## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Progress (%) | Estimated Hours | Actual Hours | Dependencies
PM-001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | High | Completed | 100% | 4 | 4
PM-002 | Requirements Gathering | John Smith | 2024-03-25 | High | In Progress | 60% | 12 | 6 | PM-001
PM-003 | Design Phase Final Review | Lisa Chen | 2024-04-10 | Medium | Not Started | 0% | 8 | 0 | PM-002
PM-004 | Development Sprint 1 | Mike Taylor | 2024-04-30 | High | Planned | 0% | 20 | 0 | PM-003
PM-005 | User Testing & Feedback | Sarah Kim | 2024-05-15 | High | Not Started | 0% | 16 | 0