## Worksheet
Task ID | Task Title | Project Name | Assigned To | Priority Level | Start Date | Due Date | Status | Estimated Hours | Actual Hours | Progress % | Dependencies | Comments | Created Date | Updated Date
TM-001 | Project Kickoff Meeting | Software Development Phase 1 | Jane Doe | High | 2024-03-15 | 2024-03-18 | Completed | 8 | 8 | 100% | -- | No comments. | 2024-03-15 | 2024-03-18
TM-002 | Requirement Gathering Session | Software Development Phase 1 | John Smith | Moderate | 2024-03-16 | 2024-03-20 | In Progress | 16 | 12 | 75% | TM-001 | Need to finalize user stories and validate with stakeholders. | 2024-03-16 | 2024-03-20
TM-003 | Design Wireframes | Software Development Phase 1 | Lisa Chen | High | 2024-03-21 | 2024-03-25 | Pending Approval | 14 | 0 | 0% | TM-002 | Wireframes to be reviewed by product manager. | 2024-03-21 | 2024-03-21
TM-004 | Develop Backend API | Software Development Phase 1 | Mike Johnson | High | 2024-03-26 | 2024-04-05 | Scheduled | 36 | 0 | 0% | TM-003, TM-005 | API integration will be tested after frontend is ready. | 2024-03-26 | 2024-03-26
TM-005 | Frontend UI Implementation | Software Development Phase 1 | Sarah Kim | Moderate | 2024-03-28 | 2024-04-10 | Scheduled | 48 | 0 | 0% | TM-004, TM-006 | UI components to align with design specs. | 2024-03-28 | 2024-03-28