## Worksheet
Task ID | Task Name | Owner | Budget (USD) | Actual Cost (USD) | Status | Start Date | End Date | Progress (%) | Priority
PM-001 | Project Initiation & Planning | John Smith | 50,000.00 | 48,750.00 | Completed | 2024-01-15 | 2024-01-31 | 100% | High
PM-002 | Resource Allocation & Team Setup | Sarah Lee | 35,000.00 | 34,200.00 | On Track | 2024-02-15 | 2024-03-15 | 85% | Medium
PM-003 | Phase One Development | Mike Johnson | 120,000.00 | 98,500.00 | In Progress | 2024-03-16 | 2024-05-31 | 65% | High
PM-004 | Risk Assessment & Mitigation | Lisa Wong | 25,000.00 | 24,150.00 | Completed | 2024-01-25 | 2024-01-30 | 100% | High
PM-005 | Final Testing & QA Review | David Chen | 40,000.00 | 39,850.00 | Scheduled | 2024-11-15 | 2024-11-30 | 0% | Medium