## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Progress (%) | Dependencies | Notes
PMT-001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | High | 100% |  | Initial project alignment and objectives set.
PMT-002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-31 | In Progress | High | 60% | PMT-001 | Stakeholder interviews scheduled.
PMT-003 | Design Phase Initiation | Michael Chen | 2024-04-01 | 2024-04-15 | Planned | Medium | 0% | PMT-002 | Waiting on final requirements.
PMT-004 | Development Planning | Lisa Wong | 2024-04-16 | 2024-05-31 | High | Medium | 10% | PMT-003 | Team to finalize architecture.
PMT-005 | Testing & Quality Assurance | Raj Patel | 2024-06-01 | 2024-06-30 | Not Started | Low | 0% | PMT-004 | Final testing to be conducted post-development.