## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Progress (%) | Comments
T001 | Project Kickoff Meeting | John Smith | High | 2024-03-15 | Completed | 100% | All stakeholders confirmed attendance.
T002 | Requirements Gathering | Sarah Johnson | High | <2024-03-25In Progress | 65% | Initial interviews with key users completed.
T003 | Design Finalization | Michael Chen | Medium | 2024-04-10 | Not Started | 0% | Waiting for approval of concept sketches.
T004 | Development Phase | Team A | High | 2024-05-01 | Not Started | 0% | Technical specifications pending.
T005 | Testing & QA | Lisa Park | High | 2024-05-20 | Not Started | 0% | No test environment available yet.