## Worksheet
Task ID | Task Name | Owner | Priority | Due Date | Status | Progress (%) | Quarterly Goal
PM-2024-Q1-001 | Project Kickoff Meeting | Alex Turner | High | 2024-03-15 | Completed | 100% | Finalize project charter
PM-2024-Q1-002 | Requirements Gathering Phase | Samira Chen | High | 2024-04-10 | In Progress | 75% | Complete stakeholder interviews
PM-2024-Q1-003 | UI/UX Design Approval | Jordan Lee | Medium | 2024-04-25 | Pending | 0% | Obtain client sign-off on design mockups
PM-2024-Q1-004 | Development Sprint 1 | Raj Patel | High | 2024-05-15 | Not Started | 0% | Deliver core feature modules
PM-2024-Q1-005 | Quarterly Risk Assessment Review | Morgan Reed | Medium | 2024-06-01 | Planned | 0% | Identify and mitigate key risks
Total Tasks: |  |  |  | 5