## Worksheet
Task ID | Task Name | Owner | Assigned To | Priority | Due Date | Status | Estimated Hours | Actual Hours | Progress (%) | Comments
T-001 | Project Kickoff Meeting | John Doe | Team A | High | 2023-10-05 | Completed | 4 | 4 | 100%
T-002 | Requirements Gathering | Sarah Lee | Team B | High | 2023-10-15 | In Progress | 8 | 3.5 | 44% | Additional stakeholder input needed.
T-003 | Design Phase Finalization | Mike Chen | Team C | Medium | 2023-11-01 | Not Started | 12 | 0 | 0% | Waiting for approval from QA team.
T-004 | Development Sprint 1 | Lisa Wang | Team D | High | 2023-11-20 | <Planned | 40 | 0 | 0% | Initial codebase setup pending.
T-005 | Testing & Quality Assurance | David Kim | Team E | High | 2023-12-10 | Not Started | 30 | 0 | 0% | Depends on development completion.