## Worksheet
Task ID | Task Name | Owner | Priority | Due Date | Status | Progress (%) | Comments
T001 | Project Kickoff Meeting | John Smith | High | 2023-10-05 | In Progress | 60% | Final agenda to be approved by 10/04.
T002 | Requirements Gathering | Sarah Lee | Medium | 2023-10-15 | Not Started | 0% | Initial workshops scheduled for 10/10.
T003 | Design Phase Finalization | Mike Chen | High | 2023-11-01 | On Hold | 35% | Client feedback pending.
T004 | Development Start | Lisa Wong | Medium | 2023-11-15 | Not Started | 0% | Waiting for final design approval.