## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Progress (%) | Comments
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | High | Completed | 100% | Meeting notes and agenda shared with team.
T002 | Requirements Gathering | Jane Smith | <>2024-04-15Medium | In Progress | 65% | Client feedback collected, draft document under review.
T003 | Design Phase Finalization | Mike Johnson | 2024-05-10 | High | Not Started | 0% | Waiting on stakeholder approval of prototype.
T004 | Development Sprint 1 | Sarah Lee | 2024-05-30 | High | In Progress | 40% | Frontend modules completed; backend integration pending.
T005 | Testing & QA Review | David Kim | 2024-06-15 | Medium | Not Started | 0% | Test cases to be developed in coordination with Dev team.