## Worksheet
Task | Assigned To | Start Date | End Date | Duration (Days) | Status | Progress (%) | Notes
Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | Completed | 100% | All stakeholders aligned on goals.
Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | 9 | In Progress | 65% | Finalizing user stories and acceptance criteria.
Design Phase | Alex Johnson | 2024-04-11 | 2024-04-25 | 15 | Planned | 0% | Wireframes and UI mockups to be developed.
Development Phase | Team A | 2024-04-26 | 2024-05-31 | 36 | Planned | 0% | Frontend and backend modules to be built.
Testing & QA | Lisa Brown | 2024-06-01 | 2024-06-15 | 15 | Planned | 0% | Functional, integration, and user acceptance testing.
Deployment & Go-Live | Operations Team | 2024-06-16 | 2024-06-16 | 1 | Planned | 0% | System goes live with monitoring in place.