## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Define Annual Project Scope | Project Manager | 01/15/2024 | Not Started | High | Finalize project goals and deliverables for the year.
Finalize Project Budget | Finance Lead | <02/01/2024 | In Progress | High | Include all departmental costs and contingency planning.
Establish Project Team Roles | HR Manager | 02/15/2024 | Not Started | Medium | Assign responsibilities and reporting lines.
Conduct Kickoff Meeting | Project Manager | 03/01/2024 | Not Started | High | Review goals, timelines, and communication protocols.
Develop Quarterly Milestone Plan | Project Manager | 04/01/2024 | Not Started | Medium | Break down annual objectives into quarterly phases.
Monitor and Review Progress | Project Manager | Monthly | Ongoing | High | Hold monthly review meetings with stakeholders.
Final Project Review and Closeout | Project Manager | 12/31/2024 | Not Started | High | Document lessons learned and celebrate achievements.