## Worksheet
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Estimated Hours | Actual Hours | Dependencies | Progress (%) | Comments | Created On | Updated On
PM-001 | Conduct project kickoff meeting with stakeholders | Sarah Johnson | High | 2023-10-05 | Completed | 4 | 4 | None | 100% | All attendees confirmed and meeting minutes drafted. | 2023-10-03 | 2023-10-05
PM-002 | Finalize project scope and requirements document | Michael Chen | High | 2023-10-15 | In Progress | 8 | 3 | PM-001 | 37.5% | Initial draft completed; feedback pending from stakeholders. | 2023-10-04 | 2023-10-10
PM-003 | Develop project timeline and Gantt chart | Emma Rodriguez | Medium | 2023-10-20 | Not Started | 6 | 0 | PM-002 | 0% | Waiting for scope document finalization. | 2023-10-05 | 2023-10-05
PM-004 | Organize risk assessment workshop | David Kim | High | 2023-10-25 | Planned | 5 | 0 | PM-003 | 0% | Schedule to be confirmed with team lead. | 2023-10-10 | 2023-10-10
PM-005 | Prepare budget forecast and cost breakdown | Lisa Thompson | Medium | 2023-10-30 | Not Started | 8 | 0 | PM-003, PM-004 | 0% | Initial cost estimates in progress. | 2023-10-15 | 2023-10-15