## Worksheet
Task | Assignee | Due Date | Priority | Status | Estimated Hours | Actual Hours | Dependencies | Comments
Conduct project kickoff meeting | John Doe | 2024-04-01 | High | Not Started | 4 | 0
Finalize project scope document | Jane Smith | <2024-04-08 | High | In Progress | 6 | 3 | Kickoff meeting complete | Clarify deliverables with stakeholders
Develop project timeline & Gantt chart | Alex Brown | 2024-04-15 | Medium | Planned | 8 | 0 | Scope document finalized
Perform risk assessment and mitigation planning | Sarah Lee | 2024-04-22 | High | Not Started | 10 | 0 |  | Include technical and budget risks
Hold weekly progress review meetings | Team Lead | Ongoing | Medium | Not Started | 2 per week | 0 | All tasks completed before meeting | Track team velocity and issue resolution