## Worksheet
Task | Assigned To | Due Date | Priority | Status | Progress (%) | Notes
Project Kickoff Meeting | Manager John Doe | 2024-04-01 | High | Pending | 0% | Confirm agenda and attendees.
Scope Document Finalization | Project Lead Sarah Lee | 2024-04-10 | High | In Progress | 65% | Final review pending stakeholder feedback.
Resource Allocation Plan | Operations Team | 2024-04-15 | Moderate | Not Started | 0% | Determine team availability and skills.
Risk Assessment Workshop | Project Manager Alex Chen | 2024-04-20 | High | Pending | 0%
Budget Approval Request | Finance Director | 2024-04-25Moderate | Not Started | 0%