## Worksheet
Quarter | Project Phase | Task | Owner | Due Date | Status | Priority
Q1 | Initiation | Finalize project charter | John Smith | 2024-03-15 | Not Started | High
Q1 | Initiation | Conduct stakeholder analysis | Anna Lee | 2024-03-25 | Not Started | Medium
Q1 | Planning | Define project scope and deliverables | Mark Thompson | 2024-04-10 | In Progress | High
Q1 | Planning | Develop detailed project schedule | Lisa Wong | 2024-04-20 | Not Started | High
Q2 | Execution | Conduct design review meetings | John Smith | 2024-06-15 | Not Started | Medium
Q2 | Execution | Begin development of MVP features | Mark Thompson | 2024-07-01 | In Progress | High
Q3 | Testing & QA | Perform unit and integration testing | Lisa Wong | 2024-09-10 | Not Started | High
Q3 | Testing & QA | Conduct user acceptance testing (UAT) | Anna Lee | 2024-10-15 | Not Started | High
Q4 | Deployment & Closure | Deploy to production environment | John Smith | 2024-12-01 | Not Started | High
Q4 | Deployment & Closure | Conduct post-project review and lessons learned | Mark Thompson | 2024-12-30 | Not Started | Medium