## Worksheet
Week | Project Name | Budget Allocation (USD) | Actual Spending (USD) | Variance (USD) | Status | Notes
Week 1 | Home Renovation Project | 500 | 420 | 80 | On Track | Materials ordered on time.
Week 2 | Home Office Setup | 300 | 285 | 15 | On Track | All equipment delivered.
Week 3 | Kitchen Upgrade | 1200 | 1150 | 50 | On Track | Work completed ahead of schedule.
Week 4 | Garden Maintenance | 200 | 230 | -30 | Over Budget | Extended landscaping work due to weather.
Week 5 | Home Security Installation | 400 | 400 | 0 | On Track | All systems installed and tested.