## Worksheet
Week | Project Name | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status | Notes
Week 1 | Website Redesign | 5,000 | 4,200 | 800 | On Track | Design finalized; development in progress.
Week 2 | Mobile App Development | 10,000 | 9,500 | 500 | On Track | UI/UX review completed.
Week 3 | Cloud Migration | 7,500 | 7,200 | 300 | On Track | Migrated core services; testing ongoing.
Week 4 | Customer Support Platform | 6,000 | 5,800 | 200 | Development phase completed.