## Worksheet
Week | Project Phase | Team Member | Task Description | Estimated Hours | Hourly Rate ($) | Total Cost ($) | Status
Week 1 | Planning & Scoping | Sarah Johnson | Define project scope, objectives, and deliverables | 10 | 80 | 800 | On Track
Week 1 | Planning & Scoping | David Lee | Conduct stakeholder interviews and requirements gathering | 12 | 80 | 960 | On Track
Week 2 | Design & Prototyping | Maria Gomez | Create wireframes and user flow diagrams | 8 | 80 | 640 | In Progress
Week 2 | Design & Prototyping | James Patel | Develop interactive prototypes and conduct usability testing | 15 | 80 | 1,200.00 | In Progress
Week 3 | Development Phase | Lisa Chen | Frontend implementation and UI development | 16 | 80 | 1,280.00 | Planned
Week 3 | Development Phase | Tom Wilson | Backend integration and API development | 20 | 80 | 1,600.00 | Planned
Total Budget for the Period: |  |  | $ |  |  | $5,520.00