## Worksheet
Week | Project Name | Objective | Start Date | End Date | Status | Key Milestones | Responsible Person | Risks & Dependencies | Progress % | Next Action Item | Meeting Notes
Week 1 | Product Launch v2.0 | Finalize product design and secure stakeholder approval | 2023-10-01 | 2023-10-15 | In Progress | UI/UX review complete, prototype approved | Jane Doe | Design change request from marketing team | 45% | Conduct design validation with QA team | Discussed feedback on navigation flow; adjust color scheme.
Week 2 | Customer Onboarding System | Deploy new onboarding module to test environment | 2023-10-08 | 2023-10-22 | On Track | Module integration complete, user testing scheduled | Mark Smith | API key access delayed by IT team | 75% | Schedule pilot user session with 5 early adopters | Users reported intuitive flow; minor bug fixes required.
Week 3 | Marketing Campaign Rollout | Launch campaign across all digital channels | 2023-10-15 | 2023-10-30 | Delayed | Campaign launch postponed due to content review | Lisa Chen | Final copy approval delayed by legal team | 20% | Resubmit campaign materials with revised compliance tags | Legal requested additional disclosures; updated content ready.
Week 4 | Team Training & Tool Setup | Complete onboarding for new team members | 2023-10-22 | 2023-11-05 | Completed | All training modules delivered, tools configured | David Lee | No significant blockers; smooth onboarding process | 100% | Begin performance review with new hires | New team members report high satisfaction with training.