## Worksheet
Week | Project Name | Start Date | End Date | Status | Owner | Key Deliverables | Milestones | Risk Assessment | Next Actions
Week 1 | Product Launch Phase | 2023-10-01 | 2023-10-07 | On Track | Jane Smith | Final UI Design Approval | Design Review, MVP Ready | Low - Minor UI Feedback | Complete design review by team lead
Week 2 | Development Sprint 1 | 2023-10-08 | 2023-10-14 | At Risk | Mark Johnson | Frontend Module Build | Module Integration Complete | Medium - Delay in API Response Time | Schedule buffer added; review with backend team
Week 3 | QA Testing Phase | 2023-10-15 | 2023-10-21 | In Progress | Lisa Chen | End-to-end Testing Report | Defect Resolution Targeted | Low - 2 Critical Bugs Identified | Fix critical bugs by end of week
Week 4 | User Training Rollout | 2023-10-222023-10-28Pending | Sophie Davis | Training Materials Finalized | Onsite Training Sessions Scheduled | None Identified | Confirm trainer availability and logistics