## Worksheet
Week | Project Phase | Key Activities | Owner | Deadlines | Status | Notes
Week 1 | Kickoff & Planning | Finalize project charter, stakeholder alignment, WBS development | Project Manager | Mon, Jan 10 | On Track | Stakeholder meeting scheduled for Friday.
Week 2 | Requirements Gathering | Conduct interviews, document user needs, finalize requirements doc | Business Analyst | Fri, Jan 14 | In Progress | Two key users confirmed for interviews.
Week 3 | Design & Prototyping | Create wireframes, prototype UI, conduct design review | UX Designer | Wed, Jan 26 | Scheduled | Prototype feedback due next week.
Week 4 | Development Start | Begin backend setup, database schema design | Development Lead | Mon, Feb 1 | Pending Approval | Design final approval pending from PM.
Week 5 | Development Phase | Frontend development, API integration, unit testing | Full Development Team | Fri, Feb 11 | In Progress | Testing to begin after integration.
Week 6 | Quality Assurance | Bug tracking, regression testing, performance checks | QA Manager | Wed, Feb 23 | Scheduled | Final QA report due before go-live.
Week 7 | User Acceptance Testing (UAT) | Conduct UAT with end users, collect feedback | Product Owner | Mon, Mar 7 | Pending | Feedback from pilot group will be shared.
Week 8 | Go-Live Preparation | Final data migration, user training, documentation | Operations Lead | Fri, Mar 18 | On Track | Go-live checklist updated.
Week 9 | Launch & Post-Launch Review | System go-live, monitor performance, collect early feedback | Project Manager | Sun, Mar 27 | Completed | Post-launch review meeting held.
Week 10 | Performance Review & Optimization | Analyze system performance, identify bottlenecks, optimize workflows | Tech Lead | Mon, Apr 5 | Planned | Optimization plan in draft.