## Worksheet
Week | Project Name | Start Date | End Date | Status | Owner | Progress (%) | Next Action | Risk Level
Week 1 | Website Redesign | 2024-04-01 | 2024-04-30 | On Track | Alex Johnson | 65% | Finalize UI mockups | Medium
Week 2 | App Development Phase 1 | 2024-04-08 | 2024-04-25 | Delayed | Sarah Lee | 30% | Fix backend integration issues | High
Week 3 | Marketing Campaign Launch | 2024-04-15 | 2024-04-30 | On Track | Mike Chen | 85% | Review analytics post-launch | Low
Week 4 | Client Onboarding Process | 2024-04-22 | 2024-05-06 | In Progress | Laura Park | 45% | Complete training documentation | Medium