## Worksheet
Week of | Project Name | Objective | Key Activities | Responsible Person | Status (✅/❌) | Deadline | Risks & Dependencies | Action Items | Notes / Observations
April 7 - April 13, 2024 | Website Redesign Phase I | Finalize UI/UX mockups and gather stakeholder feedback. | Conduct UX workshops, finalize wireframes, share with PMO. | Jane Smith | ✅ | Apr 10, 2024 | Stakeholder availability; feedback delay risk. | Follow up with design team on final mockups. | No major issues. Feedback received within deadline.
April 14 - April 20, 2024 | Mobile App Feature Development | Develop and test login and onboarding flow. | Build login module, conduct QA testing, document bugs. | Mike Johnson | ❌ | Apr 18, 2024 | API latency issues; third-party auth dependency. | Schedule emergency meeting with backend team. | Delay in API response affecting timeline.
April 21 - April 27, 2024 | Client Training Workshop | Train key client staff on new platform features. | Prepare training materials, host session, collect feedback. | Sarah Lee | ✅ | Apr 25, 2024 | No known dependencies; client schedule flexible. | Send post-training survey to participants. | All attendees completed training successfully.
April 28 - May 4, 2024 | Performance Optimization | <Improve load speed by at least 30% for core pages. | Run performance audit, optimize images and code, test results. | David Chen | ✅ | May 2, 2024 | Server load may increase during testing phase. | Migrate staging to production with backup plan. | Speed improved from 4.5s to 3.1s — goal met.
May 5 - May 11, 2024 | Stakeholder Review Meeting | Present all progress to executive board for approval. | Presentation slides, demo session, Q&A. | Jane Smith & Mike Johnson | ✅ | May 8, 2024 | Board may request changes to feature set. | Prepare change request documentation for review. | Approval granted; minor adjustments requested.