## Worksheet
Week | Project Name | Start Date | End Date | Status | Progress (%) | Key Deliverables | Risks | Owner | Next Action
Week 1 | Website Redesign | 03/04/2024 | 03/18/2024 | On Track | 65% | Wireframes approved, UI mockups ready | Design feedback delay | Sarah Chen | Finalize branding guidelines by Friday
Week 2 | App Development Phase | 03/11/2024 | 04/07/2024 | On Track | 45% | Backend API in testing, frontend design in progress | Third-party integration delays | David Lee | Schedule sprint review on Wednesday
Week 3 | Marketing Campaign Launch | 04/08/2024 | 04/29/2024 | In Progress | 30% | Social media assets ready, email campaign drafted | Budget approval pending | Lisa Park | Submit budget proposal by Thursday
Week 4 | Client Onboarding Process | 04/30/2024 | 05/13/2024 | Not Started | 0% | Process documentation, training materials | Client availability uncertain | James Wong | Schedule client meeting next week