## Worksheet
Week | Project Activities |  |  |  | Responsible Person | Deadline | Status
| Planning | Execution | Review | Risk/Issue Tracking
Week 1 | Finalize scope document | Begin team onboarding | First milestone review | No identified risks | Alex Morgan | 2023-10-07 | On Track
Week 2 | Confirm stakeholder requirements | Develop project timeline | Mid-week progress check-in | Resource availability delay (tracked) | Jordan Lee | 2023-10-14 | On Track
Week 3 | Finalize budget allocation | Conduct design workshop | Quality assurance plan review | Scope change request pending approval | Taylor Reed | 2023-10-21 | In Progress
Week 4 | Approve prototype design | Begin development phase | Monthly team sync meeting | Third-party tool integration delay (in progress) | Samira Patel | 2023-10-28 | On Track
Week 5 | Finalize change request documentation | Development sprint launch | Pre-production testing phase | Resource reallocation required (planned) | Alex Morgan | 2023-11-04 | On Track
Week 6 | Conduct risk reassessment | Complete unit testing | Review with stakeholders | No new risks identified | Jordan Lee | 2023-11-11 | Completed
Week 7 | Prepare go-live plan | Finalize deployment schedule | Final sign-off meeting | Post-launch support planning initiated | Taylor Reed | 2023-11-18 | In Progress
Week 8 | Finalize documentation | Go-live execution | Post-launch review session | All tasks completed. Project closed. |  |  | Samira Patel | 2023-11-25 | Completed