## Worksheet
Week | Project Name | Start Date | End Date | Status | Key Tasks | Owner | Progress (%) | Risks & Issues | Next Actions
Week 1 | Website Redesign | 2024-04-01 | 2024-04-30 | In Progress | UI/UX Design, Content Audit, Wireframing | Sarah Chen | 60% | Design approval delay | Reschedule design review to Friday
Week 2 | Mobile App Development | 2024-04-08 | 2024-04-25 | Planned | Backend Setup, API Integration | David Kim | 20% | Third-party API not ready | Request early access from vendor
Week 3 | Marketing Campaign Launch | 2024-04-15 | 2024-04-30 | On Track | Social Media Rollout, Email Sequence | Lisa Wang | 90% | None | Finalize analytics setup
Week 4 | Client Onboarding Process | 2024-04-22 | 2024-05-06 | Not Started | Process Documentation, Training Materials | James Reed | 0% | Client feedback not received | Initiate client meeting next week