## Worksheet
Week | Date Range | Project Goal | Key Tasks | Owner | Progress (%) | Risks & Issues | Next Steps
Week 1 | Mar 3 – Mar 9 | Launch MVP Beta | UI/UX finalization, backend integration, user testing | Sarah Chen | 80% | Server latency in testing phase | Optimize API performance; schedule QA sprint
Week 2 | Mar 10 – Mar 16 | Gather user feedback | Beta launch, collect survey responses, analyze data | James Liu | 60% | Low engagement in early users | Launch targeted outreach campaign; adjust onboarding flow
Week 3 | Mar 17 – Mar 23 | Refine product based on feedback | Feature prioritization, redesign checkout flow | Amina Diallo | 40% | Conflicting user priorities; need clarification | Host cross-functional workshop to align on key features
Week 4 | Mar 24 – Mar 30 | Plan go-to-market strategy | Marketing calendar, sales enablement, PR outreach | Daniel Park | 30% | Limited brand awareness in target market | Develop influencer partnership plan; run pilot campaign
Week 5 | Mar 31 – Apr 6 | Full product launch | Go-live, monitor performance, collect live feedback | Team Lead – Lena Kim | 0% | N/A (pre-launch) | Execute launch event and activate customer support