## Worksheet
Week | Project Name | Objective | Status | Key Deliverables | Milestone Due | Responsible Team | Risk/Issue Notes | Next Review Date
Week 1 | Product Launch Phase | Finalize UI/UX design and secure stakeholder approvals | On Track | Design mockups, user testing report | 2024-04-05 | Design & UX Team | No critical issues reported | 2024-04-19
Week 2 | Backend Integration | Integrate payment gateway and API endpoints | On Track (delayed by 1 day) | API documentation, integration logs | 2024-04-12 | Engineering Team | Minor latency in API response times | 2024-04-26
Week 3 | QA & Testing Phase | Conduct full system testing and bug resolution | In Progress | Test cases completed, bug report v2.1 | 2024-04-19 | QA Team | 3 critical bugs identified in authentication flow | 2024-04-30
Week 4 | User Onboarding Program | Develop onboarding workflow and training materialsDeliver onboarding guide and conduct pilot session | Delayed (pending stakeholder input) | Onboarding video, user checklist | 2024-04-26 | Product & Support Team | Stakeholder feedback delayed – awaiting final sign-off | 2024-05-03