## Weekly Planner - Tracking View
Project Management - Weekly Planner (Tracking View)
Date | Task Name | Owner | Status | Priority | Start Date | Due Date th> | Progress (%) th> | Notes th>
2024-04-01 | Market Research Phase Finalization | Sarah Chen | In Progress | High | 2024-03-25 | 2024-04-10 | 75% | Data collected from 3 regions; awaiting analysis.
2024-04-01 | UI/UX Design Approval | James Reed | Pending | High | 2024-03-30 | 2024-04-15 | 30% | Waiting for stakeholder feedback.
2024-04-01 | Development Sprint Kickoff | Linda Wong | Not Started | Middle | 2024-04-16 | 2024-04-30 | 0% | Team meeting scheduled for next Monday.
2024-04-01 | Client Presentation Draft | Marcus Taylor | Completed | Low | 2024-03-15 | 2024-04-05 | 100% | Presentation approved by client on 4/3.
2024-04-01 | Project Risk Assessment | Emma Brooks | In Review | High | 2024-03-28 | 2024-04-18 | 50% | Risks related to timeline and resource availability.