## Worksheet
Task | Start Date | End Date | Duration (Days) | Timeline (Months)
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Literature Review█ | █ | █
< t d style="padding:8px; font-weight:bold;">Research Design < t d >2024-03-16 < t d >2024-05-31 < t d >77█ | █ | █
< t d style="padding:8px; font-weight:bold;">Data Collection < t d >2024-06-01 < t d >2024-09-30 < t d >122█ | █ | █ | █
< t d style="padding:8px; font-weight:bold;">Data Analysis < t d >2024-10-01 < t d >2024-12-15 < t d >76█ | █ | █ | █
< t d style="padding:8px; font-weight:bold;">Reporting & Dissemination < t d >2024-12-16 < t d >2025-01-31 < t d >47█ | █
< t d style="padding:8px; font-weight:bold;">Project Closeout < t d >2025-02-01 < t d >2025-03-31 < t d >59█ | █
< t d style="padding:8px; font-weight:bold;">Total Project Duration < t d >2024-01-01 < t d >2025-03-31 < t d >456█ | █ | █ | █ | bar: Timeline (Months) Jan to Timeline (Months) Aug
< t d colspan="4" style="padding:10px; font-style:italic; text-align:right;">Legend:█ = Active Period ¦ <blank> = Inactive