## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Status | Responsible Person
Project Planning | 01/01/2024 | 31/01/2024 | 31 | 100 | Completed | Dr. Smith
Data Collection | 01/02/2024 | 31/03/2024 | 59 | 75 | In Progress | Dr. Lee
Data Analysis | 01/04/2024 | 31/05/2024 | 61 | 30 | In Progress | Dr. Chen
Manuscript Writing | 01/06/2024 | 31/07/2024 | 61 | 10 | In Progress | Dr. Smith, Dr. Lee
Paper Submission | 01/08/2024 | 15/08/2024 | 15 | 0 | Not Started | Dr. Smith
Presentation Preparation | 16/08/2024 | 31/08/2024 | 16 | 0 | Not Started | Dr. Lee
Final Review & Archiving | 01/09/2024 | 30/11/2024 | 91 | 0 | Not Started | Research Team