## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Status | Responsible Party
Project Initiation | 01/01/2024 | 15/01/2024 | 15 | Completed | Project Manager
Data Collection | 16/01/2024 | 28/02/2024 | 43 | In Progress | Research Team A
Data Analysis | 01/03/2024 | 31/03/2024 | 31 | Pending | Research Team B
Final Submission | 01/05/2024 | 05/05/2024 | 5