## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Owner | Progress (%)
Literature Review | 2024-06-01 | 2024-06-15 | 15 | Completed | Dr. Smith | 100%
Data Collection | 2024-06-16 | 2024-07-15 | 30 | In Progress | Dr. Lee | 65%
Data Analysis | 2024-07-16 | 2024-08-15 | 31 | Not Started | Dr. Chen | 0%
Draft Writing | 2024-08-16 | 2024-09-15 | 31 | Not Started | Dr. Smith | 0%
Peer Review | 2024-09-16 | 2024-09-30 | 15 | Not Started | Dr. Lee | 0%
Final Submission | 2024-10-01 | 2024-10-05 | 5 | Not Started | Dr. Chen | 0%
Total Tasks: 6 | [5 empty] | Overall Progress: 25%