## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Responsible | Status | Progress (%)
Literature Review | 2024-01-15 | 2024-02-15 | 31 | Dr. A. Smith | Completed | 100
Data Collection | 2024-02-16 | 2024-03-31 | 44 | Team Alpha | In Progress | 75
Data Analysis | 2024-04-01 | 2024-05-31 | 61 | Dr. B. Lee | Not Started | 0
Draft Writing | 2024-06-01 | 2024-07-15 | 45 | Dr. A. Smith, Dr. B. Lee | Not Started | 0
Peer Review & Revisions | 2024-07-16 | 2024-08-31 | 47 | External Reviewers | Not Started | 0
Final Submission | 2024-09-01 | 2024-09-15 | 15 | Project Lead | Not Started | 0