## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Owner | Dependencies
Literature Review | 2024-01-15 | 2024-02-15 | 31 | 100% | Dr. Smith | -
Proposal Drafting | 2024-02-16 | 2024-03-05 | 18 | 100% | Dr. Smith | Literature Review
IRB Approval | 2024-03-06 | 2024-03-25 | 19 | 85% | Research Admin | Proposal Drafting
Data Collection | 2024-03-26 | 2024-05-15 | 51 | 60% | Team A | IRB Approval
Data Analysis | 2024-05-16 | 2024-06-30 | 45 | 15% | Dr. Jones | Data Collection
Manuscript Writing | 2024-07-01 | 2024-08-15 | 46 | 5% | Dr. Smith, Dr. Jones | Data Analysis
Journal Submission | 2024-08-16 | 2024-08-31 | 16 | 0% | Dr. Smith | Manuscript Writing