## Worksheet
Task | Start Date | End Date | Duration (Days) | Owner | Status | Gantt Bar
Literature Review | 2024-01-15 | 2024-02-15 | 31 | Dr. Smith | In Progress
Experiment Design | 2024-02-16 | 2024-03-15 | 28 | Dr. Lee
Data Collection | 2024-03-16 | 2024-05-15 | 61 | Dr. Chen
Data Analysis | 2024-05-16 | 2024-07-15 | 61 | Dr. Smith
Manuscript Writing | 2024-07-16 | 2024-08-31 | 47 | Dr. Lee
Peer Review Submission | 2024-09-01 | 2024-09-15 | 15 | All Team