## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible | Status
Literature Review | 2024-01-15 | 2024-02-15 | 31 | 100 | Dr. Smith | Completed
Data Collection | 2024-02-16 | 2024-03-31 | 44 | 75 | Dr. Lee | In Progress
Data Analysis | 2024-04-01 | 2024-05-15 | 45 | 25 | Dr. Chen | Not Started
Drafting Report | 2024-05-16 | 2024-06-30 | 45 | 0 | Dr. Smith | Not Started
Review & Finalization | 2024-07-01 | 2024-7-31 | 31 | 0 | Dr. Lee & Dr. Chen | Not Started
Submission | 2024-08-01 | 2024-8-15 | 15 | 0 | All Team Members | Not Started