## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress (%) | Owner
Literature Review | 2023-10-01 | 2023-10-15 | 15 | Completed | 100 | Dr. Smith
Data Collection | 2023-10-16 | 2023-11-05 | 21 | In Progress | 75 | Dr. Lee
Data Analysis | 2023-11-06 | 2023-11-30 | 25 | Not Started | 0 | Dr. Chen
Draft Report | 2023-12-01 | 2023-12-15 | 15 | Not Started | 0 | Dr. Smith
Final Review & Submission | 2023-12-16 | 2023-12-31 | 16 | Not Started | 0 | Dr. Lee