## Worksheet
Project ID | Project Title | Principal Investigator | Department | Start Date | End Date | Funding Agency
P-001 | Neural Network Optimization for Climate Modeling | Dr. Alice Johnson | Environmental Science | 2023-01-15 | 2025-12-31 | National Science Foundation | 850,000 | In Progress | 67% | Preliminary models show 15% improvement in predictive accuracy. | Final validation phase with satellite data. | Collaboration with NOAA pending approval.
P-002 | Gene Editing in Rare Disease Therapy | Dr. Robert Kim | Biomedical Engineering | 2023-05-10 | 2026-04-30 | National Institutes of Health | 1,250,000 | In Progress | 42% | Clinical trial phase I initiated; no adverse effects reported. | Enrollment for Phase II begins Q3 2024. | IRB amendments under review.
P-003 | Sustainable Energy Storage Systems | Prof. Maria Chen | Mechanical Engineering | 2022-11-012025-10-31Department of Energy980,000In Progress78%Lithium-sulfur prototype exceeded energy density targets. | Prototype testing in grid-scale simulation. | Patent filed under USPTO #US2024-11235A1
P-004 | AI Ethics in Public Policy Frameworks | Dr. Elena Rodriguez | Sociology & Technology Studies | 2024-03-152027-03-14Andrew W. Mellon Foundation650,000In Planning12% | Preliminary literature review completed; stakeholder interviews scheduled. | Workshop with policy makers in June 2024. | Funding disbursement delayed by 3 weeks.
P-005 | Quantum Sensing for Groundwater Monitoring | Prof. James Wilson | Physics & Applied Mathematics | 2023-12-012026-11-30DARPA1,500,000In Progress | 54% | Sensor prototype functional; field trials planned in Nevada. | Field deployment Q4 2024. | Logistics approval pending DoD clearance.