## Worksheet
Week | Project Name | Principal Investigator | Objectives | Progress (%) | Milestones Achieved | Next Steps | Issues/Blockers | Resources Used | Status
1 | Neural Network Optimization | Dr. Alice Smith | Improve model accuracy by 15% | 75% | Dataset preprocessed, baseline model trained | Tune hyperparameters, run validation tests | Limited GPU availability | CUDA, TensorFlow, AWS EC2 | On Track
2 | Climate Data Modeling | Dr. Robert Chen | Predict regional rainfall patterns | 40% | Data collected from satellites | Build ML regression model, validate with historical data | Incomplete sensor data from Africa | Python, Pandas, Google Earth Engine | Delayed
3 | Genomic Sequencing Analysis | Dr. Maria Lopez | Identify mutation markers for cancer | 95% | Sequencing completed, preliminary analysis done | Publish findings, submit to journal | Awaiting ethics approval for publication | Illumina, R, Bioconductor | On Track
4 | AI Ethics Framework | Dr. James Wilson | Develop guidelines for responsible AI deployment | 25% | Literature review initiated | Conduct stakeholder interviews, draft framework | Low participation from industry partners | Qualtrics, NVivo, Word | Behind