## Worksheet
Project ID | Project Title | Principal Investigator | Start Date | End Date | Status | Budget ($) | Progress (%) | Next Milestone | Notes
P-001 | Climate Modeling Analysis | Dr. Alice Johnson | 2024-01-15 | 2025-12-31 | Active | $450,000 | 75% | Model Validation Phase | Data collection complete.
P-002 | Neural Network Optimization | Dr. Robert Chen | 2024-03-10 | 2025-08-30 | Pending Review | $320,000 | 45% | Training Dataset Finalized | Awaiting ethics approval.
P-003 | Renewable Energy Storage | Dr. Maria Santos | 2024-06-01 | 2026-05-31 | On Hold | $890,000 | 20% | Funding Approval | Waiting for grant decision.
P-004 | Genomic Data Integration | Dr. James Wilson | 2023-11-20 | 2024-11-30 | Active | $675,000 | 92% | Final Publication | Draft submitted for peer review.
P-005 | AI in Healthcare Diagnostics | Dr. Fatima Ahmed | 2024-07-01 | 2025-12-31 | Pending Review | $750,000 | 38% | Pilot Study Launch | IRB pending.