## Worksheet
Project ID | Project Name | Principal Investigator | Department | Start Date | End Date | Status | Budget ($) | Funding Source | Milestones | Current Progress (%) | Risks/Issues
P-001 | Advanced Data Analytics Framework | Dr. Alice Johnson | Data Science | 2024-01-15 | 2025-12-31 | In Progress | 750,000 | National Science Foundation | - Literature review - Model development - Pilot testing - Final validation | 65% | Delayed data access; pending IRB approval
P-002 | Renewable Energy Storage Optimization | Dr. Robert Chen | Engineering | 2024-03-10 | 2026-03-15 | Planning | 1,200,000 | Department of Energy | - Feasibility study - Prototype design - Lab testing - Field deployment | 15% | Battery supply chain delays; regulatory uncertainty
P-003 | AI in Clinical Diagnostics | Dr. Maria Garcia | Medicine | 2024-05-01 | 2027-11-30 | In Progress | 980,000 | National Institutes of Health | - Dataset collection - Algorithm training - Clinical trial Phase I - FDA submission prep | 40% | Data privacy compliance; model bias validation pending
P-004 | Urban Sustainability Mobility Model | Dr. James Wilson | Environmental Science | 2024-07-15 | 2025-11-30 | Pending Approval | 650,000 | City Planning Grant Fund | - Traffic simulation - Public survey - Policy impact modeling - Pilot city rollout | 5% | Funding disbursement delayed; stakeholder coordination pending