## Worksheet
Task Name | Principal Investigator | Start Date | End Date | Status | Priority | Budget (USD) | Progress (%)
Phase I Clinical Trial | Dr. Alice Smith | 2024-03-01 | 2024-09-30 | Active | High | $250,000 | 65%
Genomic Data Analysis | Dr. Robert Chen | 2024-04-15 | 2024-12-31 | Pending Review | Medium | $85,000 | 25%
Patient Recruitment | Dr. Maria Garcia | 2024-02-10 | 2024-08-31 | Active | High | $45,000 | 90%
Ethics Approval Submission | Dr. James Wilson | 2024-05-20 | 2024-06-30 | Pending | Medium | $5,000 | 5%
Final Report Compilation | Dr. Lisa Park | 2024-10-01 | 2024-11-30 | Not Started | High | $20,000 | 0%